## Sheet1
ID | Part Description | Specification | Supplier | Qty | PO status | Delivery Time | Payment Terms | Total Payment | Need Payment | Paid On
1 | High Definition High Frame Rate Camera | 45MP UHD CoaXpress CXP4 12 GP/s Bandwidth | JAI Cameras | 1 | PO released | 3 Weeks | 50% Advance before 25th April 2025 | 470000 | 235000 | 2025-04-22
2 | Power Cable | Power Lead 24V | JAI Cameras | 1 |  |  |  | 12600 | 6300 | 2025-04-22
3 | Tripod Adapter | ½" UNF Adapter Plate | JAI Cameras | 1 |  |  |  | 1940 | 970 | 2025-04-22
4 | 50mm Macro Lens | 50mm F Mount f3.1 Lens | HWYL | 1 | PO Pending | 3 Weeks | Advacnce | 79000 | 79000 | 2025-04-22
5 | CoaXpress Range Extender | 12Gb/s 4 Channel | Kaya Instruments | 1 | PO Pending | 3 to 4 Weeks | Waiitng for reply from Vendor We do have the quote. Negotiating for better terms. Foregin Payment Vendor | 120000 | 120000 | 2025-04-22
6 | Frame Grabber | 12Gb/s 1 Channel | Kaya Instruments | 1 |  |  |  | 65000 | 65000 | 2025-04-22
7 | SFP+ (Multi Mode Converter) | Multi-Mode SFP+ Converter | Kaya Instruments | 2 |  |  |  | 7000 | 7000 | 2025-04-22
8 | Fibre Optic Cable with LC/LC Connectors | 100m x LC Terminated OM4 Fibre Optic Cable | Kaya Instruments | 1 |  |  |  | 12200 | 12200 | 2025-04-22
9 | Lighting Cycle Timer | 1s - 60m Adjustable Timer | Selec 800 X C | 2 | PO Pending | 4 Days | Cash Item | 3000 | 3000
10 | Two Sensor Enclosure | SS 316 Enclosure |  | 1 | Vendor Searching |  |  |  |  | 2025-04-22
11 | DIN Rail | 227mm x 35mm DIN Rail | RS India | 1 | PO Released | 10 Days | Payment will be door delivery via Cheque | 334 | 334 | 2025-04-22
12 | DIN Rail Terminal Block | Pack of 10 2.5mm² DIN Rail Terminal Blocks | RS India | 1 |  | 10 Days |  | 2734 | 2734 | 2025-04-22
13 | 10A DP MCB (Incoming Supply Isolator) | 10A DP MCB | RS India | 1 |  | 10 Days |  | 691 | 691 | 2025-04-22
14 | 6A SP MCB Feed to the Edge PC and SMPSU) | 6A SP MCB | RS India | 2 |  | 10 Days |  | 582 | 582 | 2025-04-22
15 | Inlet Air Filter Assembly | Finder 7F Fan Filter 92mm x 92mm | RS India | 1 |  | 10 Days |  | 929 | 929 | 2025-04-22
16 | Extract Fan Assembly and Filter | Finder 7F Filter Fan 24V DC 92mm x 92mm | RS India | 1 |  | 10 Days |  | 6018 | 6018 | 2025-04-22
17 | Cable Glands | Pack of 25 Grey Nylon Cable Glands M16 x P1.5mm Thread | RS India | 1 |  | 10 Days |  | 1015 | 1015 | 2025-04-22
18 | 24V DC SMPSU 10A DIN Rail Mount (Camera and Extract Fan) | 85V - 264V AC I/P 10A 24V DC O/P | P&S Innovation | 1 |  | 5 Days |  | 4500 | 4500 | 2025-04-22
19 | Camera/Sensor Mount | Alzo Small Camera Wall Mount with Mini Ball Head | Tanotis | 2 | Website Purchase | 10 Days |  | 8710 | 8710
20 | Power Cable | 3 Core 1.5mm²/m | Polycab | 5 | In Stock | Instock
21 | Industrial Edge PC (Tower Format) | i7 ≥12th Gen CPU 32Gb RAM 2Tb SSD. ≥PCIe x4, Win 11 Pro | Dell | 1 | PO pending | 4 weeks | Advance | 120000 | 120000
22 | GPU |  |  |  | Amazon | 5 days |  | 65000
[8 empty] | 981253 | 673983